## Action Plan
Group 5 |  | Hospitals Coursework: Collaborative Coding Assignment
Project Summary
Aim is to develop a hospital database containing details about Doctors based at different hospitals, who are assigned a number of patients. Aspects of each patient's medical history is included, alongside relevant data related to different diseases. The database is to be created in both SQL and MS Access, and all data and relevant portfolio information included in Github.
ACTION PLAN
ACTION | RESPONSIBLE | PRIORITY | STATUS | START DATE | END DATE | NOTES
GOAL #1 Prepare plans for development of each database
Compile flowcharts for hospital database queries
Create profile of tables required and the relationships between them
Create tables for queryinig in each database:
(a) Diseases | Jenna | Medium | Complete | 2024-12-30 | 2025-01-05
(b) appointments - requires Doctors and Patients | Ross | Medium | Complete | 2024-12-30 | 2025-01-05
(c) lab results - requires Doctors, Patients and Hospital | Esther | Medium | Complete | 2024-12-30 | 2025-01-05
(d) Hospitals (including the CSV file provided) | Jenna | Medium | Complete | 2024-12-30 | 2025-01-05
(e) Doctors and patients | Emily | Medium | Complete | 2024-12-30 | 2025-01-05
(f) Medications | Ross | Medium | Complete | 2024-12-30 | 2025-01-05
(g) Prescriptions | Jenna | Medium | Complete | 2024-12-30 | 2025-01-05
GOAL #2 Build GitHub Repo
Set up GitHub and associated file plan | Jenna | High | Complete | 2025-01-10 | 2025-01-12
Write ReadMe file | Emily | Medium | Complete | 2025-01-10 | 2025-01-12
GOAL #3 Write Pseudocode and SQL queries
Complete questions 1 - 4 | Esther | Medium | Complete | 2025-01-05 | 2025-01-07
Complete questions 5 - 9 | Jenna | Medium | Complete | 2025-01-05 | 2025-01-07
Complete questions 10 - 14 | Emily | Medium | Complete | 2025-01-05 | 2025-01-07
Complete questions 15 - 19 | Ross | Medium | Complete | 2025-01-05 | 2025-01-07
Upload all SQL queries to GitHub | All | Medium | Complete | 2025-01-07 | 2025-01-07
GOAL #4 Build Microsft Access Database and test SQL queries
Upload 8x databases | Ross | Medium | Complete | 2025-01-10 | 2025-01-12
Build relationship diagram | Jenna | Medium | Complete | 2025-01-10 | 2025-01-12
Create SQL queries and test them | Jenna | Medium | Complete | 2025-01-10 | 2025-01-12

## Settings
PRIORITY OPTIONS | PROGRESS OPTIONS
High | Complete
Medium | On Hold
Low | In Progress
Not Started